# Draft timeline for the EGR 2025

| To the extent possible, flexibility will be built into various chapter timelines in discussion with authors |  |
| --- | --- |
| Month | Activities and milestones |
| January-February | - Establish Steering Committee (SC), including bringing new SC members on board - Conference call with SC to discuss new steering committee members and overall topics for the 2025 report, 15 January - Consultations with key stakeholders to ensure the assessment credibility, integrity, impartiality and relevance - Initiate recruitment of Lead Authors (LA’s) and Contributing Authors (CA’s) - Develop the draft content note, work plan and timeline for the report production - Conference call with the SC to decide on the content of the report and discuss additional lead and contributing authors, 19 February |
| March | - Lead and contributing author teams are approved by the SC and established, and contracting of LA’s is initiated - Consultations with NDC modelling groups to discuss timelines, approaches and coordination around assessments of the new NDCs as they are submitted. - Agreement on key milestone dates for intermediate NDC assessments and approach to assessment of NDCs submitted after the report cut-off date. - Working group on 1.5°C feasibility and narrative established, and first meeting held - Annotated chapter outlines are completed and shared with the SC, 20 March - Virtual SC and LA meeting to discuss annotated chapter outlines and agree on ways forward for first-order drafts, 26 March (3 hours) - Development of first order drafts commences |
| April | - Work on first order drafts continues - Identification of external reviewers commences |
| May | - First-order chapter drafts, including appendices, completed and shared with the SC, 12 May - Virtual SC and LA meeting(s) to discuss first order drafts and agree on revisions to be made prior to external review and country vetting, 20 and 21 May - External reviewers invited and country vetting process set up - Procurement of production services is initiated |
| June | - Meeting(s) in Bonn during the SBs, incl. meeting with authors and SC members who are already in Bonn (i.e. no travel costs will be reimbursed), meetings with the UNFCCC NDC SYR team, and potentially a dedicated 1.5°C feasibility and narrative meeting with broader participation, 16-20 June TBC - Revised first order drafts are completed and shared with the Secretariat, 26 June |
| July | - External review, 30 june-31 July - Country vetting, 30 june-31 July |
| August | - Authors and SC members consider the country vetting and external review comments received. - Two-day in-person SC and LA meeting in Copenhagen to discuss narrative, key messages, and chapter finalization, and to agree on science editing required to the drafts/overall report, 12-13 August. - Development of figures and infographics commences with the designer. - Authors work with the scientific editors to prepare final draft chapters, including addressing external review and country vetting comments. - Overall outreach strategy developed by UNEP. |
| September | - Final draft chapters are completed, 5 September. - Revisions and editing of final draft chapters for consistency, integrity, and language in close collaboration between the scientific editors and the lead authors, 8-29 September. - First draft of the Executive Summary (ES) completed and shared with SC and LA’s for comments, 12 September. - SC members and LA’s provide feedback on the ES, 4 September. - SC call to discuss draft ES and any final issues related to chapters, figures, etc, 16 September. - Second draft of ES shared for comments, 19 September - Editing final draft chapters for consistency, integrity, and language completed, 29 September. - Foreword completed, 29 September. - Executive Summary completed and sent for last tweaks, 29 September. - The report goes to production (language editing and layout), week of 29 September - Detailed planning of global launch and outreach events completed. |
| October | - Figures and infographics completed 6 October - Embargoed materials completed, 15 October - Production (layout and translation) completed, 21 October - Translation and layout of executive summary into 5 UN languages completed, 21 October - Editing, proofreading and layout of annexes completed in time for global launch, 21 October - Global launch of the EGR 2025, 22 October TBC - Outreach events and webinars |
| November | - Outreach events and webinars - Printing of the report ahead of COP30, week of 4 November - Outreach during COP30 in Belem, 11-24 November (side events and briefings) - Bilateral briefings and webinar(s) |
| December | - EGR internal satisfaction survey is conducted in advance of the debriefing meeting, and the external uptake survey is initiated - Meeting of the SC and LA: Debriefing and discussion of topics for the EGR 2025, 3 December |